## Sheet1
| Anju V | Deepthi Das V | Kavya R | Vidya G
DATE | TASK | TASK | TASK | TASK
| Week 1(Jul 25- Jul 31) | Week 2(Aug 01- Aug 07)
2016-07-25 | Listing of Topic | Listing of Topic | Listing of Topic | Listing of Topic
2016-07-26 | AMCAT | AMCAT | AMCAT | AMCAT
2016-07-27 | Listing of Topic | Listing of Topic | Listing of Topic | Listing of Topic
2016-07-28 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
2016-07-29 | Guide Suggestion | Guide Suggestion | Guide Suggestion | Guide Suggestion
2016-07-30 | Topic Selection | Topic Selection | Topic Selection | Topic Selection
2016-07-31
Week 2(Aug 01- Aug 07)
2016-08-01 | Topic Finalization | Topic Finalization | Topic Finalization | Topic Finalization
2016-08-02 | Search of abstraction | Search of abstraction | Scearch of abrstraction | Search of abstraction
2016-08-03 | Consolidating the collected information | Group Discussion | Group Discussion | Group Discussion
2016-08-04 | Search for existing system | Search About Home automation | Problem related to Home Automation | Search About Home automation
2016-08-05 | Search About Home automation | Usage of Raspberry pi | Search About Home automation | Usage of Home Automation
2016-08-06 | Learning about usage Raspberry Pi | Connection of Raspberry Pi | Basic concept of Raspberry Pi | Connection of Raspberry Pi
2016-08-07
Week 03(Aug 08- Aug 14)
2016-08-08 | Learrning about usage Raspberry Pi | Learrning about usage Raspberry Pi | Learrning about usage Raspberry Pi | Learrning about usage Raspberry Pi
2016-08-09 | “ | “ | “ | “
2016-08-10 | “ | “ | “ | “
2016-08-11 | “ | “ | “ | “
2016-08-12 | Guide Review | Guide Review | Guide Review | Guide Review
2016-08-13 | Progress Consolidation | Progress Consolidation | Progress Consolidation | Progress Consolidation
2016-08-14 | circuit connection based IOT | Rely circuit on Fan | Rely Circuit on Light | Rely Circuit On camera model
Week 04 (Aug 15- Aug 21)
2016-08-15 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
2016-08-16 | Videos Raspberry pi 1 | Videos Raspberry pi 2 | Videos Raspberry pi 3 | Videos Raspberry pi 4
2016-08-17 | “ | “ | “ | “
2016-08-18 | Guide Suggestion | Guide Suggestion | Guide Suggestion | Guide Suggestion
2016-08-19 | Information Consolidation | Information Consolidation | Information Consolidation | Information Consolidation
2016-08-20 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
2016-08-21 | working on Raspberry pi 1 | working on Raspberry pi 2 | working on Raspberry pi 3 | working on Raspberry pi 4
Week 05 (Aug 22- Aug 28)
2016-08-22 | Guide Suggestion | Guide Suggestion | Guide Suggestion | Guide Suggestion
2016-08-23 | Run DemoProgram | Run DemoProgram | Run DemoProgram | Run DemoProgram
2016-08-24 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
2016-08-25 | Search about Iot | uses of IoT in our life | Advantages of IoT | Need of iot
2016-08-26 | BOF Session | BOF Session | BOF Session | BOF Session
2016-08-27 | Need of IOT | PPT On IOT Implemention | PPT on Home Automation | Need of home automation
2016-08-28 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
Week 06 (Aug 30- Sep 04)
2016-08-29 | First Naukri.com Test | First Naukri.com Test | First Naukri.com Test | First Naukri.com Test
2016-08-30 | Freshers World Exam | Freshers World Exam | Freshers World | Freshers World
2016-08-31 | Guide Review | Guide Review | Guide Review | Guide Review
2016-09-01 | Internals
2016-09-02
2016-09-03
2016-09-04 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
Week 07 (Sep 05- Sep 11)
2016-09-05 | Importance of IoT | Purpose of IoT | useful of IoT | advantages of IoT
2016-09-06 | IoT basis paper1 | IoT basis paper2 | IoT basis paper3 | IoT basis paper4
2016-09-07 | Internals | Internals | Internals | Internals
2016-09-08 | Videos on Glowing LED | learning on How to Glow LED | Working on How to Glow LED | Working on How to Glow LED
2016-09-09 | Introduction of Python | Introduction of Python | Sample program on python | execution Sample program on python
2016-09-10
2016-09-11
Week 08 (Sep 12- Sep 18)
2016-09-12 | Introduction of Python | Sample Program on Python | Execution Sample program | Group Discussion
2016-09-13 | Guide Review | Guide Review | Guide Review | Guide Review
2016-09-14 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
2016-09-15 | Finding Resources | Finding Resources | Finding Resources | Finding Resources
2016-09-16 | Hardware purchase | Hardware purchase | Hardware purchase | Hardware purchase
2016-09-17 | Hardware purchase | Hardware purchase | Hardware purchase | Hardware purchase
2016-09-18 | Hardware purchase | Hardware purchase | Hardware purchase | Hardware purchase
Week 09 (Sep 19- Sep 25)
2016-09-19 | Hardware purchase | Hardware purchase | Hardware purchase | Hardware purchase
2016-09-20 | List of software Requirments | Hardware Assessment | Cost evaluation | Capital Assessment
2016-09-21 | Guide Review | Guide Review | Guide Review | Guide Review
2016-09-22 | WBD Introduction | WBD Samples | SRS Introduction | SRS Samples
2016-09-23 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
2016-09-24 | WBD Version 1 | WBD Version 1.2 | SRS Version 1 | SRS Version 1.2
2016-09-25 | WBD Version 2 | WBD Version 2.2 | SRS Version 2 | SRS Version 2.2
Week 11 (Sep 26- Oct 02)
2016-09-26 | Guide Review | Guide Review | Guide Review | Guide Review
2016-09-27 | WBD version 2 | WBD version 2.2 | SRS Version 2 | SRS Version 2.2
2016-09-28 | Guide Suggestion | Guide Suggestion | Guide Suggestion | Guide Suggestion
2016-09-29 | WBD version 2.3 | WBD version 2.4 | SRS Version 2.3 | SRS Version 2.4
2016-09-30 | Holiday | Holiday | Holiday | Holiday
2016-10-01 | Job Mela Interview | Job Mela Interview | Job Mela Interview | Job Mela Interview
2016-10-02 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
Week 12 (Oct 03- Oct 09)
2016-10-03 | WBD Structure Final Version 1 | WBD Structure Final Version 2 | SRS Function req | SRS non functional
2016-10-04 | WBD Structure Final Version Review | WBD Structure Final Version Review | SRS Final Version Review | SRS Final Version Review
2016-10-05 | Orientation Program | Orientation Program | Orientation Program | Orientation Program
2016-10-06 | Internals
2016-10-07
2016-10-08
2016-10-09 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
Week 13 (Oct 10- Oct 16)
2016-10-10 | Introduction on temperature sensor | Introduction on temperature on humidity | Introduction on motion sensor | Introduction on sound sensor
2016-10-11
2016-10-12 | Videos on temperature sensor | videos on temperature on humidty | Videos on motion sensor | videos on sound sensor
2016-10-13
2016-10-14 | working on temperature sensor | working on humidity sensor | working on motion sensor | Working on sound sensor
2016-10-15
2016-10-16
Week 14 (Oct 17- Oct 23)
2016-10-17 | Dasara Holidays | Dasara Holidays | Dasara Holidays | Dasara Holidays
2016-10-18 | Guide Review | Guide Review | Guide Review | Guide Review
2016-10-19 | WBD Structure Final Version Changes | WBD Structure Final Version Changes | SRS Final Version Changes | SRS Final Version Changes
2016-10-20 | WBD Structure Final Version Changes Review | WBD Structure Final Version Changes Review | SRS Final Version Changes Review | SRS Final Version Changes Review
2016-10-21 | HOD Approval | HOD Approval | HOD Approval | HOD Approval
2016-10-22 | Review | Review | Review | Review
2016-10-23 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
Week 15(Oct 24- Oct 30)
2016-10-24 | Hardware Assessment | Hardware Assessment | Hardware Assessment | Hardware Assessment
2016-10-25 | Guide Review | Guide Review | Guide Review | Guide Review
2016-10-26 | Hardware Component 1 study | hardware component 2 study | Hardware Component 3 Study | Hardware Compnent 4 study
2016-10-27 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
2016-10-28 | Guide Suggestion | Guide Suggestion | Guide Suggestion | Guide Suggestion
2016-10-29 | working on model 1 | working on model 2 | working on model 3 | working on model 4
2016-10-30
Week 16(Oct 31- Nov 06)
2016-10-31 | Updating SRS
2016-11-01
2016-11-02 | Guide Review | Guide Review | Guide Review | Guide Review
2016-11-03 | LED GLOW WORKING
2016-11-04
2016-11-05 | submit work to guide and HOD
2016-11-06 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
Week 17(Nov 07- Nov 13)
2016-11-07 | Lab Internals
2016-11-08
2016-11-09
2016-11-10
2016-11-11
2016-11-12
2016-11-13
Week 18(Nov 14- Nov 20)
2016-11-14 | Internals
2016-11-15
2016-11-16
2016-11-17
2016-11-18 | Search Raspberry Pi Basic Programs | Search Raspberry Pi Limitations | Raspberry Pi Advantages | Raspberry pi Disavdantages
2016-11-19 | Group Discussion
2016-11-20
Week 19(Nov 21- Nov 27)
2016-11-21 | Guide Suggestion | Guide Suggestion | Guide Suggestion | Guide Suggestion
2016-11-22 | Search Motor Control Program | Search LED Control Program | Hardware Assessment | Hardware Assessment
2016-11-23 | Execute Motor Control Program
2016-11-24
2016-11-25 | Guide Review | Guide Review | Guide Review | Guide Review
2016-11-26 | HOD Submission
2016-11-27
Week 20(Nov 28- Dec 04 )
2016-11-28 | VTU EXAMS
2016-11-29
2016-11-30
2016-12-01
2016-12-02
2016-12-03
2016-12-04
Week 21(Dec 05 – Dec 11)
2016-12-05 | VTU EXAMS
2016-12-06
2016-12-07
2016-12-08
2016-12-09
2016-12-10
2016-12-11
2016-12-12 | VTU EXAMS
2016-12-13
2016-12-14
2016-12-15
2016-12-16
2016-12-17
2016-12-18
2016-12-19 | VTU EXAMS
2016-12-20
2016-12-21
2016-12-22
2016-12-23
2016-12-24
2016-12-25
2016-12-26 | VTU EXAMS
2016-12-27
2016-12-28
2016-12-29
2016-12-30
2016-12-31
2017-01-01
2017-01-02 | VTU EXAMS
2017-01-03
2017-01-04
2017-01-05
2017-01-06
2017-01-07
2017-01-08
2017-01-09
2017-01-10 | started building house model
2017-01-11 | installation of noobs
2017-01-12 | hardware connection of raspberry pi | hardware connection of led | hardware connection of raspberry pi | hardware connection of led
2017-01-13 | learning sensors on temperature | learning sensors on motion | learning sensors on light | learning sensors on door locking
2017-01-14 | features on temp sensors | features on moton sensors | features on light sensors | features on door locking sensors
2017-01-15 | learning how to bulid the model of smart home
2017-01-16
2017-01-17
2017-01-18 | connection of raspberry pi | running the code | debugging the error | glowing of led
2017-01-19
2017-01-20 | searching about pubnub | uses of pubnub | watching videos in pubnub | installing the pubnub
2017-01-21 | Start working on login page | learning the html and css for code | watching videos on making login page | learnning code for making login page
2017-01-22 | continue on working on login page | continue learning html and css | continue on watching videos | continue on learning code
2017-01-23 | Start working on login page to store in the data base | continue learning html and css | continue on watching videos | continue on learning code
2017-01-24 | group discussion | group discussion | group discussion | group discussion
2017-01-25 | Guide Review | Guide Review | Guide Review | Guide Review
2017-01-26
2017-01-27 | started working on front end page | watching videos on front end making | learning java code for front end | learning about how to front end
2017-01-28 | started working on front end page | watching videos on front end making | learning java code for front end | learning about how to front end
2017-01-28 | started working on front end page | watching videos on front end making | learning java code for front end | learning about how to front end
2017-01-29 | started working on front end page | watching videos on front end making | learning java code for front end | learning about how to front end
2017-01-30
2017-01-31
2017-02-01
2017-02-02 | downloading Noobs | formatting ang knowing about SD card | extracting Noobs to SD card | knowing the SD card features to raspberry pi
2017-02-03 | making raspberry pi connencction to mointor | installing rasberian os | debugging the error | searching for alternate solution for error
2017-02-04 | connection of Led to raspberry pi | watching videos on Led connection to raspberrypi | correction on Led connection | watching videos to learn to connect two led at once
2017-02-05
2017-02-06 | Group Discussion | Group Discussion | Group Discussion | Group Discussion
2017-02-07 | created the Login Page | Created the Database to store Login page | created the front end page in java | Done House Model using Ice creamstick
2017-02-08 | created the Login Page | Created the Database to store Login page | created the front end page in java | Done House Model using Ice creamstick
2017-02-09 | Guide Review | Guide Review | Guide Review | Guide Review
2017-02-10 | group discussion | group discussion | group discussion | group discussion
2017-02-11 | doing IEEE paper | installing MIT software | watching videos on making an MIT app | started learning how to code for MIT App
2017-02-12
2017-02-13 | doing IEEE paper | done IEEE paper | done app using MIT app | done app using MIT app
2017-02-14 | done IEEE paper | done IEEE paper | done app using MIT app | done MIT app for bluetooth connection
2017-02-15 | setup bluetooth on raspberry pi |  | learning how to interface bluetooth to raspberry pi
2017-02-16 | Guide Review | Guide Review | Guide Review | Guide Review
2017-02-17 | started interfacing with MIT app | MIT app failed try using Blueterm app | Installed command need to run Blueterm | Started Interfacing with Blueterm app
2017-02-18 | learning about corona | watching videos about corona | started learning about lua language | watching videos to learn howto run code
2017-02-19
2017-02-20 | installation of Apache | installing of php | installing the MySql | Installing Lamp
2017-02-21 | created a Domain | Created the Local host | run the code in terminal | debugging the error
2017-02-22 | started interfacing with web app |  | SRS updated | WBS updated
2017-02-23 | Doing PPT on our topic | Doing PPT on our topic | SRS updated | upload to GitHub
2017-02-24 | Preparing for Project Review
2017-02-25 | Project Review
2017-02-26
2017-02-27 | Starting next Module ie Fan | Learning about fan module | watching videos about fan module | learming hardware connection
2017-02-28 | doing hardware connection to run a fan | connection of fan to raspberry pi | run the code in terminal | Debugging the error